# UCF Analytics & Integrated Planning (AIP)

Document Version History

| Version | Revision Notes | Author(s) | Date |
| --- | --- | --- | --- |
| 1.0 | Initial draft | Andre Watts | 8/8/2026 |

Project Identification

| Project Title: | Financial Aid Impact Study on Student Success |
| --- | --- |
| Project ID (Jira)/Name: | TBD |
| Project Manager/Lead: | TBD |
| Project Start Date: | TBD |
| Target Completion Date: | TBD |

Recommended Priority

☐ Critical
☒ High 
☐ Medium
☐ Low

AIP Strategic Pillar: Select the primary pillar.

☒ Institutional Insights & Performance

☐ Enterprise Power BI Enablement

☐ Fabric & Platform Evolution

☐ Data Governance Expansion

☐ State Reporting & DARE Optimization

☐ Skills Readiness

☐ Legacy System Decommissioning

☐ Other

Project Overview

Project Purpose

This project will develop a framework to measure the effectiveness of institutional, state, and federal financial aid programs on student success outcomes. The study will distinguish between associational and causal effects, helping university leadership understand which aid programs produce the greatest return on investment (ROI) for student success.

Problem Statement

UCF currently lacks a systematic framework for distinguishing which financial aid programs, if any, are driving improvements in student success outcomes (e.g., retention, GPA, graduation, time-to-degree) versus which are minimally related to success due to  who receives them. With a proper analysis, UCF leadership will fully understand which programs produce the greatest impact per dollar.

Project Overview/History (or “Background”)

This project aims to use statistical analysis along with descriptive analysis to historical financial aid and student outcome data, to understand impacts of institutional, state, and federal aid programs on student success and potentially estimate their relative ROI.

Strategic Alignment

UCF Strategic Objective(s)

| Strategic Objective | Alignment Description |
| --- | --- |
| Student Success | Identifies which financial aid programs most effectively improve retention, GPA, and graduation outcomes, informing better-targeted aid strategy. |
| Operational Excellence | Improves efficiency of financial aid investment by directing resources toward the programs shown to produce the greatest causal impact. |
| Data-Informed Decision Making | Directly replaces associational assumptions about aid effectiveness with rigorous causal evidence to guide resource allocation. |
| Academic Excellence | N/A |
| Research Excellence | Contributes research on financial aid effectiveness, of potential interest for understanding |

Project Goals & Objectives

Project Goals

- Develop a framework/method that distinguishes associational from causal effects of institutional, state, and federal financial aid programs on student success outcomes.

- Estimate the relative ROI of major financial aid programs on retention, GPA, graduation, and time-to-degree.

- Provide university leadership with evidence-based data on impact of programs to student outcomes.

Objectives

| Objective | Target |
| --- | --- |
| Assemble and validate a 5-10 year historical dataset covering financial aid awards (institutional, state, federal) and student outcome data. | Clean, validated analytical dataset assembled and provided by AIP |
| Apply defined scope data criteria and constraints (e.g., aid program types in scope, minimum award history). | Curated dataset meeting all documented scope criteria |
| Engineered data set to be used for analysis. | Curated set documented and reviewed with AIP. |
| Build and evaluate model(s) or algorithms to estimate aid program impact. | Model/algorithm achieves an agreed-upon threshold on sensitivity and successful metrics to measure. |
| Generate ROI estimates and comparative impact findings across financial aid programs. | Output delivered and reviewed with university leadership |
| Document empirical findings and recommendations, including benefits and limitations of the analysis. | Findings and recommendations summary delivered to AIP. |

Scope

In Scope

- Use of UCF (5-10 years) historical institutional, state, and federal financial aid award data and student outcome data.

- Curated dataset that meets an agreed upon set of criteria for inclusion.

- Both associational (descriptive) and causal analysis of aid program impact on retention, GPA, graduation, and time-to-degree.

- Delivery of a validated analytical framework falls within the agreed-upon threshold.

- Delivery of all developed code and documentation used towards the final analysis.

Out of Scope

- Individual student-level financial counseling or aid-package recommendations; this project delivers program-level findings, not individual advising.

- Aid programs/students that do not meet the agreed upon criteria for inclusion (e.g., insufficient historical award history).

Deliverables

| Deliverable | Description | Owner | Due Date |
| --- | --- | --- | --- |
| Data Requirements & Source Inventory | Documented data sources, extraction specifications, and scope/filter criteria. | AIP | TBD |
| Cleaned & Prepared Analytical Dataset | 5-10 year historical financial aid and student outcome dataset prepared and validated for modeling. | AIP | TBD |
| Feature Engineering Layer | Calculated features defined and documented for use with model. | ISC4323 Team | TBD |
| Causal & Associational Model(s) | Validated statistical models/algorithms to support framework. | ISC4323 Team | TBD |
| Model Evaluation & Sensitivity Analysis | Summary of model performance, robustness checks, benefits, and limitations. | ISC4323 Team | TBD |
| Financial Aid ROI Findings Report | Comparative ROI estimates and impact findings across institutional, state, and federal aid programs. | ISC4323 Team | TBD |
| Final Findings Presentation/Report | Summary of empirical findings | ISC4323 Team/ AIP | TBD |

Stakeholders

| Stakeholder Group | Role | Interest | Engagement Level |
| --- | --- | --- | --- |
| AIP Team | Project Execution / Governance | Delivery of accurate data for analysis and project alignment, compliance, and oversight | High / Continuous |

Roles & Responsibilities (High-Level RACI)

| Activity | AIP Leadership | AIP Data / DS | ISC4323 Team | Colleges / Units |
| --- | --- | --- | --- | --- |
| Requirements | A / R | I | C | I |
| Data Source Development | A | R | C | I |
| Testing / Model Training | A / C | I | R | I |
| Validation | A / C | I | R | I |
| Deployment | A | R | C | I |

R = Responsible | A = Accountable | C = Consulted | I = Informed

Assumptions

- The project team will have timely, approved access to required historical student and financial aid data.

- Historical data is sufficiently complete and consistent to support modeling.

- Key members of AIP are available to answer logic and definition inquiries during core engineering and development work.

Limitations

Observed performance gains may be driven by external student characteristics rather than the financial aid programs for a student.

Dependencies

| Dependency | Owner | Impact |
| --- | --- | --- |
| Access to UCF historical enrollment, course, and student data | AIP | Blocks data preparation phase and delay project |
| Data governance and security approval for use of student-level data and financial aid data. | Governance | Blocks data access and modeling start |
| Availability of project resourcing (students and/or consultant) | AIP / ISC4323 Faculty Lead | Affects project timeline and continuity |

Risks & Mitigation

| Risk | Impact | Probability | Mitigation Strategy |
| --- | --- | --- | --- |
| Incomplete or inconsistent historical data | Very High | Low | Early data profiling and cleaning; document known gaps and exclusions. |
| Delay in finalizing project staffing | High | Medium | Finalize staffing plan early; consider a phased approach if needed. |
| Delay in creating curated modeling data set | High | Medium | Frequent (weekly) standups to assess, clarify, and adjust process for creation. |
| Ambiguous assumptions for one or more aid programs, limiting valid conclusions | High | Medium | Use multiple methods where possible and clearly report which findings are a cause of success as opposed to a weak association. |
| Findings misinterpreted or overstated as fully causal by stakeholders | Medium | Medium | Clearly communicate findings in all deliverables and presentations. |
| Data governance or access delays for financial aid data | High | Medium | Engage governance, Financial Aid, and IT stakeholders early in the project. |

Success Measures (KPIs)

| Metric | Target |
| --- | --- |
| Confidence level for reported effects | 95% confidence intervals reported for all causal ROI estimates |
| Coverage of aid programs analyzed | ≥ [X]% of eligible institutional/state/federal aid programs with sufficient data included in analysis |

**The team is not limited to above success metrics and may apply additional accuracy assessment methods as needed.

Communications Plan

| Audience | Frequency | Method | Owner | Notes |
| --- | --- | --- | --- | --- |
| Executive AIP | Weekly | Status Report | AIP Project Lead |  |
| ISC4323 Team Lead | Weekly | Status Report | ISC4323 Team Lead |  |

Project Timeline & Milestones

| Milestone | Target Date |
| --- | --- |
| Charter Approval & Business Understanding: |  |
| Complete Data Delivery and Ingestion: |  |
| Complete Data Preparation & Feature Engineering: |  |
| Complete Model Development: |  |
| Complete Validation & Model Evaluation: |  |
| User Acceptance Testing: |  |
| Final Project Closeout: |  |

Approval & Authorization

| Name | Role | Signature | Date |
| --- | --- | --- | --- |
|  | AIP Director/Manager |  |  |
|  | AIP Project Lead |  |  |
|  | ISC4323 Team Lead |  |  |